## Sheet1
Sl No | Type of Crossing | District | Area | Jurisdiction | Chainage in (mtr.) | Demand Note Status | Demand Note Remarks | File note status | BG File note number | DD Filenote number | BG Status | BG request ID | BG detail | DD Status | DD PRF/DPR number | DD detail | NOC Status
1 | NATIONAL HIGHWAYS CROSSINGS | Mahasamund District | NH 353 (Bagbahra– Mahasamund) | PWD, NH Division, Raipur | 475030.41 | Not Received | Proposal submitted | [9 empty] | Not received
2 | NATIONAL HIGHWAYS CROSSINGS | Mahasamund District | NH 353 (Bagbahra– Mahasamund) | PWD, NH Division, Raipur | 479997.37 | Not Received | Proposal submitted | [9 empty] | Not received
|  |  | 2 |  | 2 | [11 empty] | Not received
| NATIONAL HIGHWAYS CROSSINGS | Raipur District | NH- (Durg-Arang) | PD, Raipur | 520337.11 | Not Received | Second site visit after updated proposal pending. | [9 empty] | Not received
|  |  | 1 |  | 1 | [11 empty] | Not received
1 | NATIONAL HIGHWAYS CROSSINGS | Nuapada District | NH 353 (Sohela – Nuapada Road) | EE, PWNH, BlangirB | 437400.97 | Not Received | Revised proposal submitted | [9 empty] | Not received
|  |  | 1 | [13 empty] | Not received
Total |  |  | 4 | [13 empty] | Not received
12 | STATE HIGHWAYS CROSSINGS | Mahasamund– District | SH-19 (Kasekera – chakchaki) | EE, PWD Division, Mahasamund | 456887.32 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
|  |  | 1 | [13 empty] | Not received
4 | STATE HIGHWAYS CROSSINGS | Raipur– District | SH-20 (Tamaseoni – Charauda) | EE, PWD Div-2 Raipur, | 520695.23 | Received |  | Approved | 72561 | 72587 | BG issued |  | 0393NDLG00304225 | DD issued |  | 917280 | Not received
|  |  | 1 | [13 empty] | Not received
25 | STATE HIGHWAYS CROSSINGS | Balangir– District | SH 42 BK BC ROAD (Bangomunda – Kantabanji) | EE, R&B Division, Kantabanji | 370328.05 | Received | [10 empty] | Not received
|  |  | 1 | [13 empty] | Not received
26 | STATE HIGHWAYS CROSSINGS | Nuapada– District | SH 3 (Sahipala – Nuaparha) | Superintending Engineer, Khariar (R&B) Division, Khariar | 434529.72 | Received |  | To be initiated | [8 empty] | Not received
|  |  | 1 | [13 empty] | Not received
Total |  |  | 4 | [13 empty] | Not received
1 | MAJOR ROADS | Mahasamund District | Mud Road (Karagula – Baniyatora) | EE.Mahasamund PWD Division | 446066.35 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
2 | MAJOR ROADS | Mahasamund District | Asphalted Road (Jhitaki – Narra) | EE.Mahasamund PWD Division | 448085.23 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
3 | MAJOR ROADS | Mahasamund District | Mud Road (Bairgaon – Saraipali) | EE.Mahasamund PWD Division | 453941.53 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
4 | MAJOR ROADS | Mahasamund District | Asphalted Road (Avradabri – Bairgaon) | EE.Mahasamund PWD Division | 477620.83 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
5 | MAJOR ROADS | Mahasamund District | Asphalted Road (Khalari – Charoda) | EE.Mahasamund PWD Division | 479236.85 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
6 | MAJOR ROADS | Mahasamund District | Asphalted Road (Kamraud – NH 353) | EE.Mahasamund PWD Division | 487735.42 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
7 | MAJOR ROADS | Mahasamund District | Mud Road (Kosmarra – Darbekera) | EE.Mahasamund PWD Division | 456350.22 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
8 | MAJOR ROADS | Mahasamund District | Asphalted Road (Boriyajhar– Keshwa) | EE.Mahasamund PWD Division | 494399.5 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
9 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bakma – Boriyajhar) | EE.Mahasamund PWD Division | 495517.09 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
10 | MAJOR ROADS | Mahasamund District | Asphalted Road (Sher – NH 353) | EE.Mahasamund PWD Division | 498499.92 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
11 | MAJOR ROADS | Mahasamund District | Asphalted Road (Baronda bazar – Laphin khurd) | EE.Mahasamund PWD Division | 506451.42 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
12 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bamhani – Chingraud) | EE.Mahasamund PWD Division | 509336.81 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
13 | MAJOR ROADS | Mahasamund District | Asphalted Road (Kosrangi – Khatti) | EE.Mahasamund PWD Division | 491380.06 | Received | Revised Demand note to be submitted with backup calculation | To be initiated | [8 empty] | Not received
14 | MAJOR ROADS | Mahasamund District | Asphalted Road (Jhitaki – Jhalmala) | EE. PMGSY Division, Mahasamund | 447291.28 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
15 | MAJOR ROADS | Mahasamund District | Asphalted Road (Kokri – Londamura) | EE. PMGSY Division, Mahasamund | 449705.09 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
16 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bairgaon – Paterapal) | EE. PMGSY Division, Mahasamund | 452471.95 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
17 | MAJOR ROADS | Mahasamund District | Asphalted Road (Kopli – Parkipali) | EE. PMGSY Division, Mahasamund | 462190.1 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
18 | MAJOR ROADS | Mahasamund District | Asphalted Road (Begbahra – Ghunchapali) | EE. PMGSY Division, Mahasamund | 466320.88 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
19 | MAJOR ROADS | Mahasamund District | Asphalted Road (Khairadera – Harnadadar) | EE. PMGSY Division, Mahasamund | 469872.66 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
20 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bhurka – Laphin kalan) | EE. PMGSY Division, Mahasamund | 503901.89 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
21 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bhalesar – Mahasamund) | EE. PMGSY Division, Mahasamund | 501935.85 | Received |  | Approved | 80840 | Not applicable | In Progress | 2781 |  | NA |  |  | Not received
22 | MAJOR ROADS | Mahasamund District | Asphalted Road (Bakma – Bitora) | EE , C.H.Jhagade Mob 9479101065 MMGSY, Mahasamund | 460205.9 | Not Received | [10 empty] | Not received
23 | MAJOR ROADS | Mahasamund District | Asphalted Road (Kosrangi – Keshwa) | EE , C.H.Jhagade Mob 9479101065 MMGSY, Mahasamund | 492060.77 | Not Received | [10 empty] | Not received
24 | MAJOR ROADS | Mahasamund District | Asphalted Road (Begbahra – Harnadadar) | Nagar Palika Baghahra | 467266.08 | Received |  | Approved | 80834 | Not applicable | In Progress | 2782 |  | NA |  |  | Not received
|  |  | 24 | 4 | 24
1 | MAJOR ROADS | Raipur District | MDR- Asphalted Road (Kumhari – Gaurbhat) | EE. PWD (B/R) Division No-2, Raipur | 514325.63 | Received |  | Approved | 72561 | 72587 | BG issued |  | 0393NDLG00304225 | DD issued |  | 917280 | Not received
2 | MAJOR ROADS | Raipur District | MDR- Asphalted Road (Bhalera – Gaurbhat) | EE. PWD (B/R) Division No-3, Naya Raipur | 515933.36 | Received |  | Approved | 72568 | 72590 | BG issued |  | 0393NDLG00304325 | DD issued |  | 917279 | Not received
3 | MAJOR ROADS | Raipur District | Asphalted Road (Gidhwa – Khapri) | E.E District PlU Chhattisgarh Rural Road Development Agency Raipur Chhattisgarh(PMGSY) | 518829.76 | Received |  | Approved | 72572 | NA | BG issued |  |  | NA |  | NA | Received
4 | MAJOR ROADS | Raipur District | Asphalted Road (Barbhata – Mokhla) | E.E District PlU Chhattisgarh Rural Road Development Agency Raipur Chhattisgarh(PMGSY) | 523384.45 | Received |  | Approved | 72572 | NA | BG issued |  |  | NA |  | NA | Received
5 | MAJOR ROADS | Raipur District | Asphalted Road (Kusumkhuta – Mokhla) | E.E District PlU Chhattisgarh Rural Road Development Agency Raipur Chhattisgarh(PMGSY) | 525648.04 | Received |  | Approved | 72572 | NA | BG issued |  |  | NA |  | NA | Received
6 | MAJOR ROADS | Raipur District | RCC Road (Dhamni – Sonpairi) | E.E District PlU Chhattisgarh Rural Road Development Agency Raipur Chhattisgarh(PMGSY) | 526756.73 | Received |  | Approved | 72572 | NA | BG issued |  |  | NA |  | NA | Received
7 | MAJOR ROADS | Raipur District | Asphalted Road (Dhamni – Gujra) | EE. PWD (B/R) Division No-1, Raipur | 528382.44 | Received |  | Approved |  | 72584 | BG issued |  | 0393NDLG00304125 | DD issued |  | 917281 | Not received
8 | MAJOR ROADS | Raipur District | Asphalted Road (Palaud – S.V.N. Cricket Stadium) | EE. PWD (B/R) Division No-1, Raipur | 533112.24 | Received |  | Approved |  | 72584 | BG issued |  | 0393NDLG00304125 | DD issued |  | 917281 | Not received
9 | MAJOR ROADS | Raipur District | Asphalted Road (Raipur – Parsada) | NRANVP Chief Executive officer Naya Raipur Division | 532386.25
10 | MAJOR ROADS | Raipur District | Asphalted Road (Asphalted Road – S.V.N. Cricket Stadium) | NRANVP Chief Executive officer Naya Raipur Division | 533582.56 | [11 empty] | Not received
11 | MAJOR ROADS | Raipur District | Asphalted Road (Kotrabhata – S.V.N. Cricket Stadium) | NRANVP Chief Executive officer Naya Raipur Division | 535353.66 | [11 empty] | Not received
12 | MAJOR ROADS | Raipur District | Asphalted Road (Mai Agri Impex Pvt. Ltd – S.V.N. Cricket Stadium) | NRANVP Chief Executive officer Naya Raipur Division | 537156.86 | [11 empty] | Not received
|  |  | 12 |  | 12 | [11 empty] | Not received
9 | MAJOR ROADS | Nuapada District | Asphalted Road (Tarborh - Naiakparha) | EE, RWD Division, Nuapada | 410074.63 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
10 | MAJOR ROADS | Nuapada District | Asphalted Road (Tarborh - Kandetara) | EE, RWD Division, Nuapada | 412020.97 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
11 | MAJOR ROADS | Nuapada District | Asphalted Road (Tarborh - Jatgarh) | EE, RWD Division, Nuapada | 412820.86 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
12 | MAJOR ROADS | Nuapada District | Asphalted Road (Tarborh - Sahajet) | EE, RWD Division, Nuapada | 414435.39 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
13 | MAJOR ROADS | Nuapada District | Asphalted Road (Patparpali - Saleparha) | EE, RWD Division, Nuapada | 418965.1 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
16 | MAJOR ROADS | Nuapada District | Asphalted Road (Sinapalli - Bhurkha Dorha) | EE, RWD Division, Nuapada | 424010.71 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
17 | MAJOR ROADS | Nuapada District | Asphalted Road (Samarsinghi - Tengnabasa) | EE, RWD Division, Nuapada | 426065.08 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
3 | MAJOR ROADS | Nuapada District | Asphalted Road (Tikraparha – Rang) | EE, RWD Division, Nuapada | 401390.59 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
4 | MAJOR ROADS | Nuapada District | Asphalted Road (Jethupali – Chaukaparha) | EE, RWD Division, Nuapada | 402826.37 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
15 | MAJOR ROADS | Nuapada District | Asphalted Road (Kurumpuri - Chhindpani) | EE, RWD Division, Nuapada | 423714.54 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
25 | MAJOR ROADS | Nuapada District | Asphalted Road (Dumarpani – Haladi) | EE, RWD Division, Nuapada | 442553.29 | Received |  | Approved | 72560 |  | BG issued |  |  | DD to be initiated |  |  | Not received
1 | MAJOR ROADS | Nuapada District | Asphalted Road (Komna – Poinr) | Superintending Engineer, Khariar (R&B) Division, Khariar | 397975.11 | Received |  | To be initiated | [8 empty] | Not received
2 | MAJOR ROADS | Nuapada District | Asphalted Road (Komna – Tikrapada) | Superintending Engineer, Khariar (R&B) Division, Khariar | 399221.46 | Received |  | To be initiated | [8 empty] | Not received
6 | MAJOR ROADS | Nuapada District | Asphalted Road (Udaynbandh – Dohelpada) | Superintending Engineer, Khariar (R&B) Division, Khariar | 404331.73 | Received |  | To be initiated | [8 empty] | Not received
14 | MAJOR ROADS | Nuapada District | Asphalted Road (Kurumpuri - Lakhna) | Superintending Engineer, Khariar (R&B) Division, Khariar | 422544.99 | Received |  | To be initiated | [8 empty] | Not received
24 | MAJOR ROADS | Nuapada District | Asphalted Road (NH-553 – Sarabong (Dumarpani Road)) | Superintending Engineer, Khariar (R&B) Division, Khariar | 441919.97 | Received |  | To be initiated | [8 empty] | Not received
22 | MAJOR ROADS | Nuapada District | Asphalted Road (Bhaira – Nuaparha) | Superintending Engineer, Khariar (R&B) Division, Khariar | 437026.95 | Received |  | To be initiated | [8 empty] | Not received
5 | MAJOR ROADS | Nuapada District | Metalled Road (Dohelparha – Chaukaparha) | BDO, Panchayat Samiti, Komana | 403431.01 | Not Received | [10 empty] | Not received
7 | MAJOR ROADS | Nuapada District | Mud Road (Pandrapathar - NH 353) | BDO, Panchayat Samiti, Komana | 404912.18 | Not Received | [10 empty] | Not received
8 | MAJOR ROADS | Nuapada District | Mud Road (Ganiari - Naiakparha) | BDO, Panchayat Samiti, Komana | 407501.18 | Not Received | [10 empty] | Not received
18 | MAJOR ROADS | Nuapada District | Asphalted Road (Sunarital - Tengnabasa) | BDO, Panchayat Samiti, Nuapada | 428070.7 | Not Received | [10 empty] | Not received
19 | MAJOR ROADS | Nuapada District | Asphalted Road (Khajurbahal - Sialati) | BDO, Panchayat Samiti, Nuapada | 429682.79 | Not Received | [10 empty] | Not received
20 | MAJOR ROADS | Nuapada District | RCC Road (Sialati - Salebhata) | BDO, Panchayat Samiti, Nuapada | 430608.43 | Not Received | [10 empty] | Not received
21 | MAJOR ROADS | Nuapada District | Asphalted Road (Padampuri – Nuaparha) | BDO, Panchayat Samiti, Nuapada | 435835.59 | Not Received | [10 empty] | Not received
23 | MAJOR ROADS | Nuapada District | Mud Road (Bhajipala – Indiranagar) | BDO, Panchayat Samiti, Nuapada | 440546.78 | Not Received | [10 empty] | Not received
|  |  | 25 |  | 25 | [11 empty] | Not received
Total |  |  | 61 | [13 empty] | Not received
15 | RAILWAY CROSSINGS | Mahasamund District | East Coast Railway (Electrified) (Begbahra RS – Bhimkoj RS) | ECOR-SBP-2024-WL-116 | 473688.89 | Not Received | 2% demand note received | [9 empty] | Not received
16 | RAILWAY CROSSINGS | Mahasamund District | East Coast Railway (Electrified) (Bhimkoj RS – Mahadi RS) | ECOR-SBP-2025-WL-08 | 480095.24 | Not Received | 2% demand note received | [9 empty] | Not received
|  |  | 2 | [13 empty] | Not received
17 | RAILWAY CROSSINGS | Raipur District | East Coast Railway (Electrified) (Mahasamund Jn. RS – Raipur Jn. RS) | SECR-R-2024-WL-143 | 538985 | Not Received | Revised proposal submitted. | [9 empty] | Not received
|  |  | 1 | [13 empty] | Not received
Total |  |  | 3 | [13 empty] | Not received
|  |  | RIVERS | [13 empty] | Not received
Not received
16 | RIVERS | Mahasamund-District | Jonk River | EE.Mahasamund Water Resources Department CG | 443996.38 | Not Received | [10 empty] | Not received
17 | RIVERS | Mahasamund-District | Kurar Nadi (River) |  | 472168.31 | Not Received | [10 empty] | Not received
|  |  | 2 | [13 empty] | Not received
18 | RIVERS | Raipur District | Mahanadi River | EE Water Management Division-1 | 511768.45 | Not Received | [10 empty] | Not received
|  |  | 1 | [13 empty] | Not received
15 | RIVERS | Nuapada-District | Kharli Nadi (River) |  | 408428.43 | [11 empty] | Received
16 | RIVERS | Nuapada-District | Jonk River |  | 443996.38 | Not Received | [10 empty] | Not received
|  |  | 2 | [13 empty] | Not received
Total |  |  | 5 | [13 empty] | Not received
39 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 458956.8 | Not Received | [10 empty] | Not received
46 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 501168.61 | Not Received | [10 empty] | Not received
47 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 503319.35 | Not Received | [10 empty] | Not received
48 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 504267.84 | Not Received | [10 empty] | Not received
49 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 505273.51 | Not Received | [10 empty] | Not received
40 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 461839.3 | Not Received | [10 empty] | Not received
41 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 464157.79 | Not Received | [10 empty] | Not received
42 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 465877.46 | Not Received | [10 empty] | Not received
43 | CANALS | Mahasamund-District | Canal | EE.Mahasamund Water Resources Department CG | 468768.11 | Not Received | [10 empty] | Not received
44 | CANALS | Mahasamund-District | Keshwa Main Canal | EE.Mahasamund Water Resources Department CG | 481701.29 | Not Received | [10 empty] | Not received
45 | CANALS | Mahasamund-District | Keshwa Main Canal | EE.Mahasamund Water Resources Department CG | 498736.15 | Not Received | [10 empty] | Not received
|  |  | 11 | [13 empty] | Not received
50 | CANALS | Raipur District | Distributary No. 17 (Canal) | EE.Water management Div-1 Raipur | 517903.58 | Not Received | [10 empty] | Not received
51 | CANALS | Raipur District | Distributary No. 18A (Canal) | EE.Water management Div-1 Raipur | 520987.72 | Not Received | [10 empty] | Not received
52 | CANALS | Raipur District | Distributary No. 19 (Canal) | EE.Water management Div-1 Raipur | 526022.91 | Not Received | [10 empty] | Not received
53 | CANALS | Raipur District | Mahanadi Main Canal | EE.Water management Div-1 Raipur | 526489.8 | Not Received | [10 empty] | Not received
54 | CANALS | Raipur District | Canal | EE Water Resources Department Minor Raipur District | 531505.95 | Received | FDR needs to be submitted as per demand note, Finance wants demand note in form of BG, Finance to confirm whether FDR can be submitted or not. | To Be initiated | [8 empty] | Not received
|  |  | 5 | [13 empty] | Not received
34 | CANALS | Nuapada-District | Dohelparha Minor Canal | SE, Irrigation Balangir Division, Nuapada | 404314.75 | [11 empty] | Received
35 | CANALS | Nuapada-District | Dhanujhola Distributary Canal | SE, Irrigation Balangir Division, Nuapada | 405288.73 | [11 empty] | Received
36 | CANALS | Nuapada-District | Sundar Left Main Canal | SE, Irrigation Balangir Division, Nuapada | 408829.39 | [11 empty] | Received
37 | CANALS | Nuapada-District | Canal | SE, Irrigation Balangir Division, Nuapada | 434755.27 | [11 empty] | Received
38 | CANALS | Nuapada-District | Upper Jonk Right Canal | SE, Irrigation Balangir Division, Nuapada | 439263.46 | [11 empty] | Received
5
Total |  |  | 21
174 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 446789.18 | Not Received | [10 empty] | Not received
175 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 449394.22 | Not Received | [10 empty] | Not received
176 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 455504.26 | Not Received | [10 empty] | Not received
177 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 457102.8 | Not Received | [10 empty] | Not received
178 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 458320.76 | Not Received | [10 empty] | Not received
179 | NALAs | Mahasamund-District | Urai Nala | EE.Mahasamund Water Resources Department CG | 463318.07 | Not Received | [10 empty] | Not received
180 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 474572.53 | Not Received | [10 empty] | Not received
181 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 476668.75 | Not Received | [10 empty] | Not received
182 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 478405.16 | Not Received | [10 empty] | Not received
183 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 478460.39 | Not Received | [10 empty] | Not received
184 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 485668.11 | Not Received | [10 empty] | Not received
185 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 496077.73 | Not Received | [10 empty] | Not received
186 | NALAs | Mahasamund-District | Sitli Nala | EE.Mahasamund Water Resources Department CG | 508898.52 | Not Received | [10 empty] | Not received
187 | NALAs | Mahasamund-District | Sitli Nala | EE.Mahasamund Water Resources Department CG | 510495.28 | Not Received | [10 empty] | Not received
188 | NALAs | Mahasamund-District | Nala | EE.Mahasamund Water Resources Department CG | 510694.94 | Not Received | [10 empty] | Not received
|  |  | 15 | [13 empty] | Not received
189 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 512969.31 | Not Received | [10 empty] | Not received
190 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 514731.51 | Not Received | [10 empty] | Not received
191 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 515882.77 | Not Received | [10 empty] | Not received
192 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 519005.64 | Not Received | [10 empty] | Not received
193 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 522912.39 | Not Received | [10 empty] | Not received
194 | NALAs | Raipur District | Nala | EE Water Management Division-1 | 527931.41 | Not Received | [10 empty] | Not received
195 | NALAs | Raipur District | Kulhan Nala | EE Water Resources Department Minor Raipur District | 529661.06 | Received | FDR needs to be submitted as per demand note, Finance wants demand note in form of BG, Finance to confirm whether FDR can be submitted or not. | To be Initiated | [8 empty] | Not received
196 | NALAs | Raipur District | Nala | EE Water Resources Department Minor Raipur District | 537006.1 | Received | FDR needs to be submitted as per demand note, Finance wants demand note in form of BG, Finance to confirm whether FDR can be submitted or not. | To be Initiated | [8 empty] | Not received
| NALAs | Raipur District | Palaud Stap Dam Canal | EE Water Resources Department Minor Raipur District | 530761.28 | Received | FDR needs to be submitted as per demand note, Finance wants demand note in form of BG, Finance to confirm whether FDR can be submitted or not. | To be Initiated | [8 empty] | Not received
|  |  | 9 | [13 empty] | Not received
Total |  |  | 24 | [13 empty] | Not received
36 | FOREIGN PIPELINE | Raipur District | Water Pipeline |  | 538431.74 | Not Received | [10 empty] | Not received
| FOREIGN PIPELINE | Raipur District | Water Pipeline | [13 empty] | Not received
1
Total |  |  | 1
1 | MINOR ROADS | Nuapada District | Cart Track (Poiner – Kamna) | BDO, Panchayat Samiti, Komana | 398554.11 | [11 empty] | Recieved
2 | MINOR ROADS | Nuapada District | Cart Track (Fields – Fields) | BDO, Panchayat Samiti, Komana | 398798.03 | [11 empty] | Recieved
3 | MINOR ROADS | Nuapada District | Cart Track (Fields – Asphalted Road) | BDO, Panchayat Samiti, Komana | 399184.58 | [11 empty] | Recieved
4 | MINOR ROADS | Nuapada District | Cart Track (Fields – Asphalted Road) | BDO, Panchayat Samiti, Komana | 399464.72 | [11 empty] | Recieved
5 | MINOR ROADS | Nuapada District | Cart Track (Fields – Mahulbhata) | BDO, Panchayat Samiti, Komana | 399839.44 | [11 empty] | Recieved
6 | MINOR ROADS | Nuapada District | Cart Track (Fields – Tikraparha) | BDO, Panchayat Samiti, Komana | 401161.21 | [11 empty] | Recieved
7 | MINOR ROADS | Nuapada District | Cart Track (Fields – Fields) | BDO, Panchayat Samiti, Komana | 405418.39 | [11 empty] | Recieved
8 | MINOR ROADS | Nuapada District | Cart Track (Pandrapathar - NH 353) | BDO, Panchayat Samiti, Komana | 406039.19 | [11 empty] | Recieved
9 | MINOR ROADS | Nuapada District | Cart Track (Canal - Fields) | BDO, Panchayat Samiti, Komana | 406809.81 | [11 empty] | Recieved
10 | MINOR ROADS | Nuapada District | Cart Track (Naiakparha - Reddy para) | BDO, Panchayat Samiti, Komana | 407977.46 | [11 empty] | Recieved
11 | MINOR ROADS | Nuapada District | Cart Track (Naiakparha - Reddy para) | BDO, Panchayat Samiti, Komana | 408789.19 | [11 empty] | Recieved
12 | MINOR ROADS | Nuapada District | Cart Track (Fields - NH 353) | BDO, Panchayat Samiti, Komana | 411030.44 | [11 empty] | Recieved
13 | MINOR ROADS | Nuapada District | Cart Track (Tarborh - Jatgarh) | BDO, Panchayat Samiti, Komana | 413183.82 | [11 empty] | Recieved
14 | MINOR ROADS | Nuapada District | Cart Track (Gohirapadar - Sahajet) | BDO, Panchayat Samiti, Komana | 415668.59 | [11 empty] | Recieved
15 | MINOR ROADS | Nuapada District | Cart Track (NH 353 - Sahajet) | BDO, Panchayat Samiti, Komana | 416639.74 | [11 empty] | Recieved
16 | MINOR ROADS | Nuapada District | Cart Track (Palsipani - Sahajet) | BDO, Panchayat Samiti, Komana | 417416.08 | [11 empty] | Recieved
17 | MINOR ROADS | Nuapada District | Cart Track (Bankibahar - Sahajet) | BDO, Panchayat Samiti, Komana | 418069.68 | [11 empty] | Recieved
18 | MINOR ROADS | Nuapada District | Cart Track (Bankibahar - Fields) | BDO, Panchayat Samiti, Komana | 418113.48 | [11 empty] | Recieved
19 | MINOR ROADS | Nuapada District | Cart Track (Patparpali - Borpadar) | BDO, Panchayat Samiti, Komana | 419539.72 | [11 empty] | Recieved
20 | MINOR ROADS | Nuapada District | Cart Track (Kariaparha - Sankaraparha) | BDO, Panchayat Samiti, Komana | 420611.83 | [11 empty] | Recieved
21 | MINOR ROADS | Nuapada District | Cart Track (Kurumpuri - Thakurpali) | BDO, Panchayat Samiti, Komana | 421458.91 | [11 empty] | Recieved
22 | MINOR ROADS | Nuapada District | Cart Track (Kurumpuri - Thakurpali) | BDO, Panchayat Samiti, Komana | 421703.99 | [11 empty] | Recieved
23 | MINOR ROADS | Nuapada District | Cart Track (Fields - Thakurpali) | BDO, Panchayat Samiti, Komana | 421869.99 | [11 empty] | Recieved
24 | MINOR ROADS | Nuapada District | Cart Track (Sinapalli - Bhurkha Dorha) | BDO, Panchayat Samiti, Komana | 423902.27 | [11 empty] | Recieved
25 | MINOR ROADS | Nuapada District | Cart Track (Fields - Samarsinghi) | BDO, Panchayat Samiti, Komana | 425614.63 | [11 empty] | Recieved
26 | MINOR ROADS | Nuapada District | Cart Track (Fields - Samarsinghi) | BDO, Panchayat Samiti, Komana | 425629.74 | [11 empty] | Recieved
27 | MINOR ROADS | Nuapada District | Cart Track (Khajurbahal - Tengnabasa) | BDO, Panchayat Samiti, Komana | 426798.96 | [11 empty] | Recieved
28 | MINOR ROADS | Nuapada District | Cart Track (Fields - Sialati) | BDO, Panchayat Samiti, Nuapada | 430186.72 | Not Recieved | [10 empty] | Not received
29 | MINOR ROADS | Nuapada District | Cart Track (Fields - Sialati) | BDO, Panchayat Samiti, Nuapada | 430298.77 | Not Recieved | [10 empty] | Not received
30 | MINOR ROADS | Nuapada District | Cart Track (Paraskhal - Ghati R.F) | BDO, Panchayat Samiti, Nuapada | 430991.82 | Not Recieved | [10 empty] | Not received
31 | MINOR ROADS | Nuapada District | Cart Track (Asphalted Road - Ghati R.F) | BDO, Panchayat Samiti, Nuapada | 431234.84 | Not Recieved | [10 empty] | Not received
32 | MINOR ROADS | Nuapada District | Cart Track (Salebhata – Nawapara Road RS) | BDO, Panchayat Samiti, Nuapada | 433615.58 | Not Recieved | [10 empty] | Not received
33 | MINOR ROADS | Nuapada District | Cart Track (Thakur Nuaparha – Silda Nala) | BDO, Panchayat Samiti, Nuapada | 437686.76 | Not Recieved | [10 empty] | Not received
34 | MINOR ROADS | Nuapada District | Cart Track (Sakhatora – Silda Nala) | BDO, Panchayat Samiti, Nuapada | 438252.86 | Not Recieved | [10 empty] | Not received
35 | MINOR ROADS | Nuapada District | Cart Track (Sakhatora – Service Road) | BDO, Panchayat Samiti, Nuapada | 439220.48 | Not Recieved | [10 empty] | Not received
36 | MINOR ROADS | Nuapada District | Cart Track (Mud Road – Dumarpani) | BDO, Panchayat Samiti, Nuapada | 440615.47 | Not Recieved | [10 empty] | Not received
37 | MINOR ROADS | Nuapada District | Cart Track (Mud Road – Dumarpani) | BDO, Panchayat Samiti, Nuapada | 440865.07 | Not Recieved | [10 empty] | Not received
38 | MINOR ROADS | Nuapada District | Cart Track (Asphalted Road – Nandpur) | BDO, Panchayat Samiti, Nuapada | 441977.11 | Not Recieved | [10 empty] | Not received
39 | MINOR ROADS | Nuapada District | Cart Track (Kolada – Jonk River) | BDO, Panchayat Samiti, Nuapada | 443739.39 | Not Recieved | [10 empty] | Not received
|  |  | 39 | [13 empty] | Not received
Total |  |  | #REF! | [13 empty] | Not received
1 | MINOR ROADS | Mahasamund District | Cart Track (Karagula – Parkom) | Gram Panchayat Parkom | 445095.11 | [11 empty] | Received
2 | MINOR ROADS | Mahasamund District | Cart Track (Karagula – Baherabhatha) | Gram Panchayat Parkom | 446525.14 | [11 empty] | Received
3 | MINOR ROADS | Mahasamund District | Cart Track (Jhitaki – Jhalmala) | Gram Panchayat Jhiki | 447862.64 | [11 empty] | Received
4 | MINOR ROADS | Mahasamund District | Cart Track (Jhitaki – Fields) | Gram Panchayat Jhiki | 447968.07 | [11 empty] | Received
5 | MINOR ROADS | Mahasamund District | Cart Track (Mudpar – Bhatapara) | Gram Panchayat Jhiki | 449117.85 | [11 empty] | Received
6 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Asphalted Road) | Gram Panchayat Jhiki | 449480.27 | [11 empty] | Received
7 | MINOR ROADS | Mahasamund District | Cart Track (Junwani – Paterapal) | Gram Panchayat Paterapali | 451333.63 | [11 empty] | Received
8 | MINOR ROADS | Mahasamund District | Cart Track (Junwani – Paterapal) | Gram Panchayat Paterapali | 451667.21 | [11 empty] | Received
9 | MINOR ROADS | Mahasamund District | Cart Track (Kosmarra – Fields) | Gram Panchayat Kasekera | 456591.05 | [11 empty] | Received
10 | MINOR ROADS | Mahasamund District | Cart Track (Chakchaki – Mahadeva) | Gram Panchayat Kasekera | 457600.29 | [11 empty] | Received
11 | MINOR ROADS | Mahasamund District | Cart Track (Birura – Bhunjiyapara) | Gram Panchayat Kuliya | 458765.48 | [11 empty] | Received
12 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Bakma) | Gram Panchayat Bakma | 460517.34 | [11 empty] | Received
13 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Ghunchapali) | Gram Panchayat Ghunchapali Kalan | 463937.59 | [11 empty] | Received
14 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Fields) | Nagar Palika Baghahra | 468637.37 | [11 empty] | Received
15 | MINOR ROADS | Mahasamund District | Cart Track (Khairadera-Bagbahara) | Nagar Palika Baghahra | 468646.32 | [11 empty] | Received
16 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Harnadadar) | Nagar Palika Baghahra | 469072.44 | [11 empty] | Received
17 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Harnadadar) | Gram Panchayat Harnadadar | 470160.84 | [11 empty] | Received
18 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Harnadadar) | Gram Panchayat Harnadadar | 470457.24 | [11 empty] | Received
19 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Patherapali) | Gram Panchayat Patherapali | 472664.79 | [11 empty] | Received
20 | MINOR ROADS | Mahasamund District | Cart Track (Kashibahra – Bahardih) | Gram Panchayat Kashibahra BK | 475837.81 | [11 empty] | Received
21 | MINOR ROADS | Mahasamund District | Cart Track (Kashibahra – Bahardih) | Gram Panchayat Kashibahra BK | 475870.55 | [11 empty] | Received
22 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Fields) | Gram Panchayat Khallari | 480539.8 | [11 empty] | Received
23 | MINOR ROADS | Mahasamund District | Cart Track (Charoda – Fields) | Gram Panchayat Marar Kashibahra | 480879.92 | [11 empty] | Received
24 | MINOR ROADS | Mahasamund District | Cart Track (Parkipali – NH 353) | Gram Panchayat Bhaluchuha | 485434.89 | [11 empty] | Received
25 | MINOR ROADS | Mahasamund District | Cart Track (Mamabhancha – NH 353) | Gram Panchayat Mamabhancha | 487072.55 | [11 empty] | Received
26 | MINOR ROADS | Mahasamund District | Cart Track (Mamabhancha – NH 353) | Gram Panchayat Mamabhancha | 487390.62 | [11 empty] | Received
27 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Fields) | Gram Panchayat Mamabhancha | 488308.21 | [11 empty] | Received
28 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Pachera) | Gram Panchayat Mamabhancha | 488772.99 | [11 empty] | Received
29 | MINOR ROADS | Mahasamund District | Cart Track (Fofiya – Pachera) | Gram Panchayat Mamabhancha | 489696.94 | [11 empty] | Received
38 | MINOR ROADS | Mahasamund District | Mud Road (Charoda – Kashibahra) | Gram Panchayat Marar Kashibahra | 483037.96 | [11 empty] | Received
39 | MINOR ROADS | Mahasamund District | Mud Road (Nawagaon – Ghunchapali) | Gram Panchayat Ghunchapali | 464323.21 | [11 empty] | Received
40 | MINOR ROADS | Mahasamund District | Mud Road (Bhatapara – Junwani) | Gram Panchayat Jhiki | 450873.75 | [11 empty] | Received
41 | MINOR ROADS | Mahasamund District | Mud Road (Junwani – Paterapal) | Gram Panchayat Paterapali | 451974.77 | [11 empty] | Received
42 | MINOR ROADS | Mahasamund District | Mud Road (Birura – Tongopani) | Gram Panchayat Kuliya | 458761.21 | [11 empty] | Received
43 | MINOR ROADS | Mahasamund District | Mud Road (Bairgaon – NH353) | Gram Panchayat Avradabri | 477202.3 | [11 empty] | Received
25 | MINOR ROADS | Mahasamund District | Mud Road (Sonaputti – Ghunchapali) | Nagar Palika Ghunchapali | 463661.52 | [11 empty] | Received
45 | MINOR ROADS | Mahasamund District | Mud Road (Parkom – Kolada) | Gram Panchayat Parkom | 444360.26 | [11 empty] | Received
46 | MINOR ROADS | Mahasamund District | Mud Road (Kosmarra – Fields) |  | 456786.96 | [11 empty] | Received
30 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Salebhata) | Gram Panchayat Sher | 497602.95 | Not Received | [10 empty] | Not received
31 | MINOR ROADS | Mahasamund District | Cart Track (Fields – Bhalesar) | Gram Panchayat Sher | 499967.8 | Not Received | [10 empty] | Not received
44 | MINOR ROADS | Mahasamund District | Mud Road (Salebhata – Sher) | Gram Panchayat Sher | 498064.91 | Not Received | [10 empty] | Not received
32 | MINOR ROADS | Mahasamund District | Cart Track (Mongra – Nawapara) | Gram Panchayat Bhalesar | 500624.87 | Not Received | [10 empty] | Not received
33 | MINOR ROADS | Mahasamund District | Cart Track (Khaira – Bhalesar) | Gram Panchayat Bhalesar | 502405.05 | Not Received | [10 empty] | Not received
34 | MINOR ROADS | Mahasamund District | Cart Track (Bhurka – Bhalesar) | Gram Panchayat Bhalesar | 503083.22 | Not Received | [10 empty] | Not received
35 | MINOR ROADS | Mahasamund District | Cart Track (Laphin Khurd – Fields) | Gram Panchayat Laphin Khurd | 507778.89 | Not Received | [10 empty] | Not received
36 | MINOR ROADS | Mahasamund District | Cart Track (Chingraud – Fields) | Gram Panchayat Chingraud | 510923.49 | Not Received | [10 empty] | Not received
37 | MINOR ROADS | Mahasamund District | Cart Track (Chingraud – Fields) | Gram Panchayat Chingraud | 511236.1 | Not Received | [10 empty] | Not received
|  |  | 47 | [13 empty] | Not received
1 | MINOR ROADS | Raipur District | Cart Track (Kumhari – Gaurbhat) | Gram Panchayat Kumhari | 514191.49 | Not Received | [10 empty] | Not received
2 | MINOR ROADS | Raipur District | Cart Track (Pahanda – Gaurbhat) | Gram Panchayat Gaurbhat | 515104.76 | Not Received | [10 empty] | Not received
3 | MINOR ROADS | Raipur District | Cart Track (Pahanda – Gaurbhat) | Gram Panchayat Gaurbhat | 515125.71 | Not Received | [10 empty] | Not received
4 | MINOR ROADS | Raipur District | Cart Track (Bhalera – Gidhwa) | Gram Panchayat Bhalera | 517078.39 | Not Received | [10 empty] | Not received
5 | MINOR ROADS | Raipur District | Cart Track (Distributary canal No. 18A – Charauda) | Gram Panchayat Charauda | 521514.4 | Not Received | [10 empty] | Not received
6 | MINOR ROADS | Raipur District | Cart Track (Barbhata – Charauda) | Gram Panchayat Charauda | 521594 | Not Received | [10 empty] | Not received
7 | MINOR ROADS | Raipur District | Cart Track (Mokla – Fields) | Gram Panchayat Mokhala | 523736.77 | Not Received | [10 empty] | Not received
8 | MINOR ROADS | Raipur District | Cart Track (Dhamni – Fields) | Gram Panchayat Dhamni | 529490.03 | Not Received | [10 empty] | Not received
9 | MINOR ROADS | Raipur District | Cart Track (Parsada – Palaud) | Gram Panchayat Palaud | 531658.56 | Not Received | [10 empty] | Not received
10 | MINOR ROADS | Raipur District | Cart Track (Parsada – Palaud) | Gram Panchayat Palaud | 531997.9 | Not Received | [10 empty] | Not received
11 | MINOR ROADS | Raipur District | Cart Track (Asphalted Road – CRPF Camp) | Gram Panchayat Palaud | 533025.04 | Not Received | [10 empty] | Not received
12 | MINOR ROADS | Raipur District | Cart Track (Asphalted Road – Senoh) | Gram Panchayat Sendh | 534022.61 | Not Received | [10 empty] | Not received
13 | MINOR ROADS | Raipur District | Cart Track (Asphalted Road – Senoh) | Gram Panchayat Sendh | 534429.5 | Not Received | [10 empty] | Not received
14 | MINOR ROADS | Raipur District | Cart Track (Asphalted Road – Sector 5) | Gram Panchayat Sendh | 536259.05 | Not Received | [10 empty] | Not received
15 | MINOR ROADS | Raipur District | Mud Road (Parsada – Palaud) | Gram Panchayat Palaud | 530927.62 | Not Received | [10 empty] | Not received
16 | MINOR ROADS | Raipur District | Cart Track (Asphalted Road – Naya Raipur) | Gram Panchayat Chhatouna | 537555.16 | Not Received | [10 empty] | Not received
|  |  | 16 | [13 empty] | Not received
Total |  |  | 63 | [13 empty] | Not received